## 2018
Name | Salman Raees
Department | Development
Designation | Senior Back-end Developer
2018-01-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| Property Match | Owner | http://107.6.184.93/MatchPropertyDirect/ | https://projects.zoho.com/portal/fleekbiz#taskdetail/1081581000000058119/1081581000000482001/1081581000000815053 | 0 | 2018-01-01 | 2018-01-11 | 2018-01-02 | 2018-01-10 | Passed | New Work on Property Match project below point is done. 1. Add Property for Seller > Map is still not working based on location. 2. Crop Feature not working for photos 3. DELETE PROPERTY should not be an working option until SELLER has paid for a subscription. In the event they are not happy. 4. When Changing profile information keeps asking to make a username .. when we should just use emails as the user. | I am faced the issue when client requirement change Image cropping function in the project because this functon already work fine
| Customer Area Development | Owner | http://107.6.184.93/fleekbizportal/ | https://projects.zoho.com/portal/fleekbiz#taskdetail/1081581000000905181/1081581000000905209/1081581000000905231 | 0 | 2018-01-16 | 2018-01-31 |  |  | Passed | 1) Create user (if user does not exist then user create and auto generated password and sending user login details and link through the email) 2) Logo Details 3) Sample Images upload (single or multiple option) 4) Logo Type (Manage with admin and show customer for selection to order process) 5) Logo Usage (Manage with admin and show customer for selection to order process) 6) Font Type (Manage with admin and show customer for selection to order process) 7) Overall Feel (Manage with admin and show customer for selection to order process) 8) Additional Details 9) Helpful Images upload (single or multiple option) 10) Pricing and package (Manage with admin and show customer for selection to order process) 11) Payment Add-on 12) Order Summary 13) Apply Coupon on order processing 14) Strip Gateway Integration 15) Final Checkout and pay
2018-02-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| Property Match | Owner | https://www.matchpropertydirect.com/ | https://projects.zoho.com/portal/fleekbiz#dashboard/1081581000000058119 | 0 |  |  |  |  | Passed | Working on new update as per client requirments | Client want to add some new functionality in the site that functionality implementation have a some challenges face | 1) Implementation of currency converter which is change all price to the whole site as per current rate 2) Customization of chat feature buyer to buyer chat and seller to buyer chat 3) In the chat feature clien want to add feature buyer chat to the specific seller which is reached to the property 4) During a image croppping feature client want to edit image show in cropping area.
| Camper | Contributor | [7 empty] | Passed | Start from the scratch and complete as per client requirements | This site complete on very short time period | This site complete ver short time period and we achive the main functionality in the site
| Logex | Contributor | http://107.6.184.93/logex/ | https://projects.zoho.com/portal/fleekbiz#dashboard/1081581000000999013 | 0 |  |  |  |  | Passed
| Customer Area Development | Owner | http://107.6.184.93/fleekbizportal/ | https://projects.zoho.com/portal/fleekbiz#dashboard/1081581000000905181 | 0 |  |  |  |  | Passed | 1- The admin area should have an option to export data to excel. 2- The different steps of order process should have different URL's/ Pages instead of one page.
2018-03-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| Property Match | Owner | https://www.matchpropertydirect.com/ | https://projects.zoho.com/portal/fleekbiz#dashboard/1081581000000058119 | 0 |  |  |  |  | Passed | Working on new update as per client requirments | Client want to add some new functionality in the site that functionality implementation have a some challenges face | 1) Implementation of currency converter which is change all price to the whole site as per current rate 2) Customization of chat feature buyer to buyer chat and seller to buyer chat 3) In the chat feature clien want to add feature buyer chat to the specific seller which is reached to the property 4) During a image croppping feature client want to edit image show in cropping area.
| Camper | Contributor | [7 empty] | Passed | Start from the scratch and complete as per client requirements | This site complete on very short time period | This site complete ver short time period and we achive the main functionality in the site
| Sugar House | Owner | http://184.154.2.170/ | https://projects.zoho.com/portal/fleekbiz#dashboard/1081581000001154335 | 0 |  |  |  |  | Passed | Hi, I wanted to see if you can help me with an emergency project. I have a big problem with the current sugarhousebanners.com site, I can no longer process credit cards. My credit card processor updated the TLS version which requires my host to move my site to a new Virtual Private Server. Unfortunately my outdated php code will not work on the new VPS and needs some updating. Can you help me update the current site? Here is the description from the hosting company: We had your site running on the VPS briefly this morning, but noticed some problems so we switched it back. There are some errors in your cart. It appears some of your code uses a now removed php option called "register globals". Newer php versions (which are the standard on newer servers running the TLS version you need) no longer support register globals. It should be easy to solve however - your developer will know how to fix. In short you just need to specify where the variable is being pulled from (usually $_GET or $_POST The errors are at: Notice: Undefined index: promocode in /home/memongo23/www/cart.php on line 58 Notice: Undefined index: convert in /home/memongo23/www/cart.php on line 92 Notice: Undefined variable: onload in /home/memongo23/www/cart.php on line 208 Notice: Undefined variable: order_number in /home/memongo23/www/cart.php on line 208 Notice: Undefined variable: register_grand_total in /home/memongo23/www/cart.php on line 208
| Customer Area Development | Owner | http://107.6.184.93/fleekbizportal/ | https://projects.zoho.com/portal/fleekbiz#dashboard/1081581000000905181 | 0 |  |  |  |  | Passed | 1- The admin area should have an option to export data to excel. 2- The different steps of order process should have different URL's/ Pages instead of one page.
| Refferal Trust | Owner | http://107.6.184.93/referaltrust/ | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000001286131/customview/6 | 0 |  |  |  |  | Passed | Presently: Once in the control panel of the user (professional), when you want to make a new referral, you click on: NEW REFERRAL Then you enter the clients information, click on NEXT and only then, you can choose the banker out of the displayed list. We would like to: When clicking on NEW REFERRAL, the list of bankers to be displayed, and then on next screen we can enter the information of the client we are referring.
2018-04-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| Refferal Trust | Owner | http://107.6.184.93/referaltrust/ | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000001286131/customview/6 | 0 |  |  |  |  | Passed
| Property Match | Owner | https://www.matchpropertydirect.com/ | https://projects.zoho.com/portal/fleekbiz#dashboard/1081581000000058119 | 0 |  |  |  |  | Passed | Working on new update as per client requirments | Client want to add some new functionality in the site that functionality implementation have a some challenges face | Change amazon gift voucher send to user after 10 successful subscribure
| Sugar House | Owner | http://184.154.2.170/ | https://projects.zoho.com/portal/fleekbiz#dashboard/1081581000001154335 | 0 |  |  |  |  | Passed | Resolve all issues of old site and start new site from the scratch
| Logo Design Dock | Owner | http://107.6.184.93/fleekbizportal/ | https://projects.zoho.com/portal/fleekbiz#dashboard/1081581000000905181 | 0 |  |  |  |  | Passed | Phase 2 Start add new features and functionality
2018-05-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| Property Match | Owner | https://www.matchpropertydirect.com/ | https://projects.zoho.com/portal/fleekbiz#dashboard/1081581000000058119 | 0 |  |  |  |  | Passed | working on client new requirement and done currency converter | Customization of currency convertor
| Sugar House | Owner | http://184.154.2.170/ | https://projects.zoho.com/portal/fleekbiz#dashboard/1081581000001154335 | 0 |  |  |  |  | Passed | Working on client new requirement shopping cart done | two types of shopping cart embeding in the site | Calculations and checkout module on diffrenet types of products .
2018-06-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| Sugar House | Owner | http://184.154.2.170/ | https://projects.zoho.com/portal/fleekbiz#dashboard/1081581000001154335 | 0 |  |  |  |  | Passed | Working on client new requirement shopping cart done | two types of shopping cart embeding in the site | Calculations and checkout module on diffrenet types of products .
2018-07-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| Sugar House | Owner | http://199.250.201.124/~sugarhouse/ | https://projects.zoho.com/portal/fleekbiz#dashboard/1081581000001154335 | 0 |  |  |  |  | Passed | Working on client new requirements. | two types of shopping cart embeding in the site | Calculations and checkout module on diffrenet types of products .
| Only Fans | Owner | http://199.250.201.124/~onlyfans | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000001491077/customview/6 | 0 |  |  |  |  | Passed | Its social media site. | 1) Subscription plan - And off those subscriptions the house gets 20%. Needs some way to track this. 2) Users can have a free account anytime, but for them to earn money, they have to set there feed to private by setting their monthly subscription fee. 3) Following is free. but once a subscription is setup, those free followers must now pay in order to continue to view the post. All post, past and present go dark once subscription is setup 4) Also need a transaction page - where we can showcase the payouts as per subscriptions | 1) Subscription plan - And off those subscriptions the house gets 20%. Needs some way to track this. 2) Users can have a free account anytime, but for them to earn money, they have to set there feed to private by setting their monthly subscription fee.
2018-08-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| Only Fans | Owner | http://199.250.201.124/~onlyfans | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000001491077/customview/6 | 0 |  |  |  |  | Passed | Its social media site. | 1) Subscription plan - And off those subscriptions the house gets 20%. Needs some way to track this. 2) Users can have a free account anytime, but for them to earn money, they have to set there feed to private by setting their monthly subscription fee. 3) Following is free. but once a subscription is setup, those free followers must now pay in order to continue to view the post. All post, past and present go dark once subscription is setup 4) Also need a transaction page - where we can showcase the payouts as per subscriptions | 1) Subscription plan - And off those subscriptions the house gets 20%. Needs some way to track this. 2) Users can have a free account anytime, but for them to earn money, they have to set there feed to private by setting their monthly subscription fee.
2018-09-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| Only Fans | Owner | http://199.250.201.124/~onlyfans | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000001491077/customview/6 | 0 |  |  |  |  | Passed | Its social media site. | 1) Subscription plan - And off those subscriptions the house gets 20%. Needs some way to track this. 2) Users can have a free account anytime, but for them to earn money, they have to set there feed to private by setting their monthly subscription fee. 3) Following is free. but once a subscription is setup, those free followers must now pay in order to continue to view the post. All post, past and present go dark once subscription is setup 4) Also need a transaction page - where we can showcase the payouts as per subscriptions | 1) Subscription plan - And off those subscriptions the house gets 20%. Needs some way to track this. 2) Users can have a free account anytime, but for them to earn money, they have to set there feed to private by setting their monthly subscription fee.
| Online Solar | Owner | 199.250.201.124/~solar/ | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000001983095/customview/6 | 0 |  |  |  |  | Passed |  | Web Flow: Screen 1 – Homepage/Welcome Page: 1. Shows the Welcome page where Customer will be able to watch the video (Will be provided by Client) about services and will be able to put their Email and will get notification through automatic email system. Screen 2 – Registration Page: 1. Customer will be able to register themselves with the webapp by putting their Name, Email, Phone no. 2. After filling out the form they will receive the SMS confirmation code on the number they put and will confirm their identity by putting the code they will receive. Screen 3 – Address Confirmation Page: 1. Will use the functionality of Google map and can drop the pin to their exact location. Screen 4 – System Selector Offer Page: 1. Customer will be able to see the product and can customize it according to their requirements. (Size, Color Etc. will be provided by Client). Screen 5 – System Confirmation Page: 1. On this page Customer will be able to confirm their order (timers will be placed on the order Example: 10 hours left with 50% off) 2. Then Customer will proceed with payment using Credit Card (PayPal, Stripe) Screen 6 – Schedule a visit: 1. Customer will schedule a visit through Acquity Calendar API 2. Customer will have an option to upload their utility bill. Screen 7 – Order Confirmation and One Time Offer Page: 3. Customer will receive the order confirmation code (Webapp will auto-generate that) 4. They will see other products as well (as a onetime offer with the timer). Screen 8 – Multiple OTO’s Confirmation: 1. If customer select any OTO or Multiple OTO’s they will see this screen to get a confirmation notification and they will be charged manually by their credit card details which they will provide on System Confirmation page. 2. Webapp must post a database the order details. (Client will give us the script). Screen 9 – Thankyou Page: 1. Will be based on the referenced shared by Client. 2. Customer will also have a survey form on this page so, they can fill out for their online shopping
| Sugar Houseq | Owner | http://199.250.201.124/~sugarhouse/ | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000001154335/customview/6 | 0 |  |  |  |  | Passed |  | working on updates
2018-10-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| PropertiMatch | Owner | http://propertimatch.craftedium.xyz | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000058119 | 0 | 2017-07-10 | 2017-07-29 |  |  | Passed | Admin panel bugs,seller and buyer dashboard,payment system and searching module in laravel project | Seller and buyer dashboard module and chat between seller and buyer and integerate strip payment module in this site | custom vaidation of form and gallery
| SpokePhone | Owner | http://spokephone.craftedium.xyz/ | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000305299 | 0 | 2017-09-20 | 2017-10-06 |  |  | Passed | Client want to 2nd phase embeding on site he want to 1) Show two tables of data to visitors that relate to the costs they will have to take and make a call in their selected country. 2) New page on the site to allow people to work out their Total Cost of Ownerwhip (TCO), and see typical ROI. | New page on the site to allow people to work out their Total Cost of Ownerwhip (TCO), and see typical ROI.
| Piedpipertravel-DL | Contributor | http://portal.fleekbiz.com/projectID/flyer.jpg | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000317093 | 0 | 2017-10-02 | 2017-10-12 |  |  | Passed | 1) Fix my login as it seems corrupted. It logs me in ok, but then it keeps asking me to login again! 2) Adding the ability to delete and edit existing reservation forms and information forms.
| Call Me Loco | Contributor | http://callmeloco.com | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000293061 | 0 | 2017-10-26 | 2017-10-26 |  |  | Passed | The email response template will be sent as a reply to them. In the email response template, we have 3 fields which need to be filled automatically through website DB. When someone fills out the form on Callmeloco.com/promo. The three fields including NAME, Login, Password. The website is going to take the name from The form that will be filled from the customer. the website will take the login and password from the Excel sheet that I attached
| Trend Box | Owner | http://trendbox.craftedium.xyz/ | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000408031 | 0 |  |  |  |  | Passed | Trendbox is a membership website based on monthly subscriptions for the users. User will have to sign up to access the website and they will get access to their dashboard to further explore the website.this part is wrong. They can explore any part of the website except “get one pages” and the user control panel pages. Users will use the dashboard to answer “user preferences” questions and to like “loved items” (will be added by admin). Users could also see their past deliveries and if they want to return any products then they could use “refund option” under same section of the website. This is overall concept of the website.
2018-11-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| Piedpipertravel-DL | Contributor | http://portal.fleekbiz.com/projectID/flyer.jpg | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000317093 | 0 | 2017-10-02 | 2017-10-12 |  |  | Passed | 1) Fix my login as it seems corrupted. It logs me in ok, but then it keeps asking me to login again! 2) Adding the ability to delete and edit existing reservation forms and information forms.
| PropertiMatch | Owner | http://propertimatch.craftedium.xyz | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000058119 | 0 | 2017-07-10 | 2017-07-29 |  |  | Passed | Admin panel bugs,seller and buyer dashboard,payment system and searching module in laravel project | Seller and buyer dashboard module and chat between seller and buyer and integerate strip payment module in this site | custom vaidation of form and gallery
| Trend Box | Owner | http://trendbox.craftedium.xyz/ | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000408031 | 0 |  |  |  |  | Passed | Trendbox is a membership website based on monthly subscriptions for the users. User will have to sign up to access the website and they will get access to their dashboard to further explore the website.this part is wrong. They can explore any part of the website except “get one pages” and the user control panel pages. Users will use the dashboard to answer “user preferences” questions and to like “loved items” (will be added by admin). Users could also see their past deliveries and if they want to return any products then they could use “refund option” under same section of the website. This is overall concept of the website.
2018-12-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| PropertiMatch | Owner | http://propertimatch.craftedium.xyz | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000058119 | 0 | 2017-07-10 | 2017-07-29 |  |  | Passed | Working on client new requriements . | Merging old functionality with new functionality
| Trend Box | Owner | http://trendbox.craftedium.xyz/ | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000408031 | 0 |  |  |  |  | Passed | Working on client new changes
Note on D6: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F6: Created by Resource
Note on D54: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F54: Created by Resource
Note on D102: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F102: Created by Resource
Note on D150: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F150: Created by Resource
Note on D198: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F198: Created by Resource
Note on D246: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F246: Created by Resource
Note on D294: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F294: Created by Resource
Note on D342: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F342: Created by Resource
Note on D390: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F390: Created by Resource
Note on D438: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F438: Created by Resource
Note on D486: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F486: Created by Resource
Note on D534: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F534: Created by Resource

## 2017
Name | Salman Raees
Department | Development
Designation | Senior Back-end Developer
2017-01-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| abc.com - complete development |  | http://www.xyz32432.com | [6 empty] | Passed | simple development, PSD to Wordpress - 10 pages |  | custom vaidation of form and gallery
| jewllery store - logo design |  | http://portal.fleekbiz.com/projectID/logo.jpg | [6 empty] | Passed | 5 unique concepts given
| music event - flyer design |  | http://portal.fleekbiz.com/projectID/flyer.jpg | [7 empty] | 1 concept designed
| xyz.com - website fixing |  | http://www.xyz12342.com | [7 empty] | backend fixing of the site |  | custom functions coding for items listing etc.
| research based article writing - 800 words |  | \\server\writer\abc\article.docx | [7 empty] | Article writing |  | new topic for me to research, client liked in 1st attempt
| xyz.com - website copywriting - 5000 words |  | \\server\writer\abc\copywriting.docx | [7 empty] | website content
2017-02-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| abc.com - complete development |  | http://www.xyz32432.com | [6 empty] | Passed | simple development, PSD to Wordpress - 10 pages |  | custom vaidation of form and gallery
| jewllery store - logo design |  | http://portal.fleekbiz.com/projectID/logo.jpg | [6 empty] | Passed | 5 unique concepts given
| music event - flyer design |  | http://portal.fleekbiz.com/projectID/flyer.jpg | [7 empty] | 1 concept designed
| xyz.com - website fixing |  | http://www.xyz12342.com | [7 empty] | backend fixing of the site |  | custom functions coding for items listing etc.
| research based article writing - 800 words |  | \\server\writer\abc\article.docx | [7 empty] | Article writing |  | new topic for me to research, client liked in 1st attempt
| xyz.com - website copywriting - 5000 words |  | \\server\writer\abc\copywriting.docx | [7 empty] | website content
2017-03-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| abc.com - complete development |  | http://www.xyz32432.com | [6 empty] | Passed | simple development, PSD to Wordpress - 10 pages |  | custom vaidation of form and gallery
| jewllery store - logo design |  | http://portal.fleekbiz.com/projectID/logo.jpg | [6 empty] | Passed | 5 unique concepts given
| music event - flyer design |  | http://portal.fleekbiz.com/projectID/flyer.jpg | [7 empty] | 1 concept designed
| xyz.com - website fixing |  | http://www.xyz12342.com | [7 empty] | backend fixing of the site |  | custom functions coding for items listing etc.
| research based article writing - 800 words |  | \\server\writer\abc\article.docx | [7 empty] | Article writing |  | new topic for me to research, client liked in 1st attempt
| xyz.com - website copywriting - 5000 words |  | \\server\writer\abc\copywriting.docx | [7 empty] | website content
2017-04-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| Orthodontist | Contributor | http://www.xyz32432.com | https://www.craftedium.com/portal/index.php/tasksComments?tasks_id=980&projects_id=11 | 0 | 2017-03-07 | Apr 06, 2017 |  |  | Passed | Landing page and 8 social graphics | is ki site already bani hui thi aur humnay new wordpress install kar k landing page bana diya tha aur us ka header footer bhi alag tha is ki live site se isi liye ab is landing page ko uski live site may emebed karna tha isi liye may nay sare option ko waha dobara se banaya aur apnay aur theme k layout k hissab se us ko waisay hi one by one set kia tha jaisay layout design and develope hua tha.tak iski live site kharab na ho aur jo humnay landing page banaya hai woh bhi embed ho jaye.
| Any Party | Owner | http://anyparty.co.uk/ | https://www.craftedium.com/portal/index.php/tasksComments?tasks_id=1017&projects_id=10 | 0 | 2017-03-15 | 2017-04-04 |  |  | Passed | The website allows a customer to post a job and then Businesses owners/service providers bid on the job to win it.once the winning business is chosen i would like the customer to have to pay a 10% deposit to me as a booking confirmation.once the 10% is paid by the customer, he/she will be able to see the businesses owners contact details and the business will be able to see the customers contact details. | Both customers and service providers can see their public profiles BUT they cannot contact each other until a customer has hired a service provider. Once I, (site admin) has received the 10% amount of agreed amount b/w both parties they can see their contact details on their public profile links and can contact directly or meet. | Theme coding modify also database modification because this theme does not meet client requirment so I do the code in this theme and creating a tables
| Skyhaq-Medical | Owner | http://www.skyhaqmedical.com/ | https://www.craftedium.com/portal/index.php/tasksComments?tasks_id=1054&projects_id=10 | 0 | 2017-03-26 | 2017-04-22 |  |  | Passed | Setup theme and change content,images and videos where the client give.
| Ucellmobile.com | Owner | http://ucell.craftedium.xyz/ | https://www.craftedium.com/portal/index.php/tasksComments?tasks_id=872&projects_id=11 | 0 | 2017-02-06 | 2017-03-14 |  |  |  | Client want to this site sell,repair and buy mobile phone s | Copy all coding and functions of cellntrade.com site and embeding new web site ucell.Changes all functions class and javascripting functionality
| Tavant Velox | Contributor | http://tavantvelox.com/ | [7 empty] | Provided Email sending code and validation of client side code for Tavant Velox's static version to Hassam
| Kiwicraftbeer.nz | Owner | http://kiwicraftbeer.nz/ | https://www.craftedium.com/portal/index.php/tasksComments?tasks_id=1063&projects_id=11 | 0 | 2017-03-28 | 2017-04-11 |  |  | Passed | 1)First of all move site to staging server 2)Update wordpress version of client final web as well. 3)Integrate PayPal to Website 4)Email and Contact Form 5)Embed Seo Optimization Plugin 6)Home page changes 7)Modify Rviews Pugin 8)Google Map Integration 9)Twitter feed show | 1)Rviews Pugin issue (Modify review plugin) 2)Google Map Integration (Change google map) 3)Twitter feed show (Create a twitter shortcode) | 1) Working on Google map api and GEO Location changes and working on that as per client requirment Show popup notify get current location if yes show highlighted 50km radius and if no show default location also show two seprate category users with diffrent flags. 2) Twitter Plugin (Modify twitter plugin and embed my coding for creating twitter shortcode that show any where twitter feeds) 3) Theme code customization because this theme using typescrpiting 4) Review Plugin (Modification in plugin)
| Eye First | Contributor | http://www.firstkey.com/webinar/ | https://www.craftedium.com/portal/index.php/tasksComments?tasks_id=1013&projects_id=10 | 0 |  |  |  |  | Passed | 1) Modify Gravity Form Plugin 2) Embed gravity hooks 3) Show thanks message in popup and passing forms values | 1) Modify Gravity Form Plugin 2) Embed gravity hooks 3) Show thanks message in popup and passing forms values
| Are you Harp Eligble | Contributor | http://harp.craftedium.xyz/demo/ | https://www.craftedium.com/portal/index.php/tasksComments?tasks_id=1049&projects_id=10 | [6 empty] | 1) Gravity Form passing all fields in next page 2) issues resolve steps progress slider | 1) Gravity Form passing all fields in next page 2) issues resolve steps progress slider
2017-05-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| Kiwicraftbeer and craftbeoir | Owner | https://www.kiwicraftbeer.nz https://www.craftbeoir.com/ | http://portal.craftedium.com/index.php/tasksComments?tasks_id=1063&projects_id=11 | 0 | 2017-03-28 | 2017-04-11 | 2017-05-01 | 2017-05-17 | Passed | 1) Integrate GEO Location API 2) Creating Facebook and Twitter shortcode which is fetch user feeds when admin just enter a username 3) Creating a shortcode customize area define in the back-end panel when the admin just putting the shortcode and show user feed in the specific item and the styling is not disturbed 4) Installing SSL Certificate in this project 5) Paypal Payment method integrate in the packages 6) Creating custom Reviews section in the item | Integrate GEO Location API :- 1) Customizing data show on the map 2) custom icon show on the map 3) specific user show in the map 4) specific categories images and data show in pin popup 5) set condition on default map and geo location map 6) Show user on gelocation map SSL Certificate :- 1) checking and working on SLL install on this site Paypal Payment method:- 1) Integrate code on typescripting coding Reviews section:- 1) Modification in the plugin as per client requirement show rating system | 1) Integrate GEO Location API 2) SSL Certificate 3) Paypal Payment method 4) Reviews section
| flytpaths.com | Owner | http://flytpaths.craftedium.xyz | http://portal.craftedium.com/index.php/tasksComments?tasks_id=1138&projects_id=11 | 0 | 2017-05-02 | 2017-05-16 | 2017-05-10
| Find Tix | Contributor | http://www.find-tix.net | ------------------------------------------- | 0 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | Passed | In this site Malware attack on worpdress core files so I am resolve this issue
| Find Tix | Contributor | http://www.find-tix.net | ------------------------------------------- | 0 | 2017-05-16 | 2017-05-16 | 2017-05-19 | 2017-05-19 | Passed | Configure Backup-buddy and ithemesecurity plugin
| Jetstreamguttering | Contributor | http://www.jetstreamguttering.com/ | http://portal.craftedium.com/index.php/tasksComments?tasks_id=1165&projects_id=11 | 0 | 2017-05-20 | 2017-05-23 |  |  | Passed | In this site Malware attack on worpdress core files so I am resolve this issue
| Gospel Light | Contributor | http://gospellight.craftedium.xyz/ | http://portal.craftedium.com/index.php/tasksComments?tasks_id=1000&projects_id=11 | 0 | 2017-03-10 | 2017-05-22 |  |  |  | All audio files are uploaded in resource page.
2017-06-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| flytpaths.com | Owner | http://flytpaths.craftedium.xyz | http://portal.craftedium.com/index.php/tasksComments?tasks_id=1138&projects_id=11 | 0 | 2017-05-02 | 2017-05-16 | 2017-05-10 |  | Passed | simple development, PSD to Wordpress - 10 pages
| Paragon - Mortgage Broker Portal | Owner | http://paragon.craftedium.xyz/ | http://portal.craftedium.com/index.php/tasksComments?tasks_id=1174&projects_id=11 | 0 | May 23, 2017 | 2017-06-21 | 2017-05-27 |  | Passed | Whole project is custom development 1) Both Signup Modules (Bank Rep / Real Estate broker). 2) Login Modules. 3) Forgot Password. 4) Bank Rep Profile Over view and edit and save changes. 5) Real Estate broker Profile Over view and edit and save changes. 1) Referral - Mortgage Broker (Client's info Module). 2) Emailing module in every process. 3) Accept Referral Module 4) Share This module 5) Show List of Referrals | This site is convert into Multilingual language | This site is convert into Multilingual language each and everything change into own code
| Simeks | Owner | http://Simeks.com | http://portal.craftedium.com/index.php/tasksComments?tasks_id=1190&projects_id=10 | 0 | 2017-05-30 | 2017-06-01 | 2017-06-01 | 2017-06-01 | Passed | Recently changed the hosting from Amazon to blue host.The random characters appear on several pages The only change is fixing the random characters that are appearing but they appear in multiple pages
| Hemamobile | Contributor | http://hema-mobile.blogspot.com/ | http://portal.craftedium.com/index.php/tasksComments?tasks_id=1196&projects_id=10 | 0 | 2017-06-03 | 2017-06-05 | 2017-06-06 | 2017-06-06 | Passed | 1. Replace the slider image with the image attached 2. Hide the portfolio section
| Find-tix | Contributor | http://www.find-tix.com/ | http://portal.craftedium.com/index.php/tasksComments?tasks_id=859&projects_id=11 | 0 | Jun 30, 2017 | 2017-06-30 | 2017-06-30 | 2017-06-30 | Passed | Remove virus on whole site and live again with configuration security plugin | Searching of viruses on whole files and hacking scripts
| one of | Contributor | http://oneof.craftedium.xyz/ | http://portal.craftedium.com/index.php/tasksComments?tasks_id=1125&projects_id=11 | 0 |  |  |  |  | Passed | Woocommerce modification shopping cart | create a new page in shopping cart.Wich is show a custom content of the specific product then product add cart
| capitaldealersolutions | Contributor | http://capitaldealersolutions.craftedium.xyz/ | http://portal.craftedium.com/index.php/tasksComments?tasks_id=1193&projects_id=11 | 0 |  |  |  |  | Passed | Remove virus on whole site and live again with configuration security plugin | Searching of viruses on whole files and hacking scripts
2017-07-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| flytpaths.com | Owner | http://flytpaths.craftedium.xyz | http://portal.craftedium.com/index.php/tasksComments?tasks_id=1138&projects_id=11 | 0 | 2017-05-02 | 2017-05-16 | 2017-05-10 |  | Passed | simple development, PSD to Wordpress - 10 pages
| Referral-trust.com - Mortgage Broker Portal | Owner | http://paragon.craftedium.xyz/ | https://projects.zoho.com/portal/fleekbiz#projectfeed/1081581000000047293 | 0 | 2017-07-19 | 2017-08-04 | 2017-08-04 | 2017-08-04 | Passed | Whole project is custom development 1) Both Signup Modules (Bank Rep / Real Estate broker). 2) Login Modules. 3) Forgot Password. 4) Bank Rep Profile Over view and edit and save changes. 5) Real Estate broker Profile Over view and edit and save changes. 1) Referral - Mortgage Broker (Client's info Module). 2) Emailing module in every process. 3) Accept Referral Module 4) Share This module 5) Show List of Referrals | This site is convert into Multilingual language | This site is convert into Multilingual language each and everything change into own code
| SpokePhone - Developmen | Contributor | http://spokephone.xyz/ | https://projects.zoho.com/portal/fleekbiz#projectfeed/1081581000000047693 | 0 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | Passed | Pricing Page development that show price on country wise through ajax do not reload a page .Make a csutom admin panel all countries and rates enter in the backend | Client want to all data Import through excel sheet
| PropertiMatch (Laravel Project) | Owner | http://propertimatch.craftedium.xyz/ | https://projects.zoho.com/portal/fleekbiz#projectfeed/1081581000000058119 | 0 | 2017-07-10 | 2017-07-29 |  |  | Passed | Project is complete redesigning of the property portal. The project was under development with a big India-based software house but the client didn't like the work and their communication. | This is Laravel framework but I do this.
2017-08-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| PropertiMatch.com - Real Estate Portal Redesign & Development - 14584970 | Owner | https://projects.zoho.com/portal/fleekbiz#projectfeed/1081581000000058119 | http://propertimatch.craftedium.xyz/ | 0 | 2017-07-10 | 2017-07-29 |  |  | Passed | Admin panel bugs,user dashboard,payment system and searching module in laravel project | This is Laravel framework but I do this. | Searching and working on new platform
| Referral-trust.com - Mortgage Broker Portal - 14061056 | Owner | http://107.6.154.186/~craftedi/paragons/ | https://projects.zoho.com/portal/fleekbiz#projectfeed/1081581000000047293 | 1 | 2017-07-19 | 2017-08-04 | 2017-08-04 | 2017-08-04 | Passed | Whole project is custom development 1) Both Signup Modules (Bank Rep / Real Estate broker). 2) Login Modules. 3) Forgot Password. 4) Bank Rep Profile Over view and edit and save changes. 5) Real Estate broker Profile Over view and edit and save changes. 1) Referral - Mortgage Broker (Client's info Module). 2) Emailing module in every process. 3) Accept Referral Module 4) Share This module 5) Show List of Referrals | This site is convert into Multilingual language | This site is convert into Multilingual language each and everything change into own code
| SykoBeats.com - Revamp + Custom PHP | Owner | http://sykobeats.com/ | https://projects.zoho.com/portal/fleekbiz#projectfeed/1081581000000070475 | 1 | 2017-07-19 | 2017-08-04 |  |  | Passed | This is custom PHP project that user sale own beats and he want to upload beat on our server. | customization and modification on media player and play and pause functionality on external buttons
| Integrity Website | Contributor | http://intergrity.craftedium.xyz/ | https://projects.zoho.com/portal/fleekbiz#dashboard/1081581000000215323 | 0 | 2017-08-23 | 2017-09-07 |  |  | Passed | working on searching with ajax functionality
2017-09-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| PropertiMatch | Owner | http://propertimatch.craftedium.xyz | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000058119 | 0 | 2017-07-10 | 2017-07-29 |  |  | Passed | Admin panel bugs,seller and buyer dashboard,payment system and searching module in laravel project | Seller and buyer dashboard module and chat between seller and buyer and integerate strip payment module in this site | this is new plateform so I am reading and searching in this plateform and working onit
| Referral-trust | Owner | http://referral-trust.com/ | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000047293 | 0 | 2017-07-19 | 2017-08-04 | 2017-08-04 | 2017-08-04 | Passed | Whole project is custom development 1) Both Signup Modules (Bank Rep / Real Estate broker). 2) Login Modules. 3) Forgot Password. 4) Bank Rep Profile Over view and edit and save changes. 5) Real Estate broker Profile Over view and edit and save changes. 1) Referral - Mortgage Broker (Client's info Module). 2) Emailing module in every process. 3) Accept Referral Module 4) Share This module 5) Show List of Referrals | This site is convert into Multilingual language | This site is convert into Multilingual language each and everything change into own code
| SykoBeats | Owner | http://sykobeats.com/ | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000070475 | 0 | 2017-07-19 | 2017-08-04 |  |  | Passed | This is custom PHP project that user sale own beats and he want to upload beat on our server. | customization and modification on media player and play and pause functionality on external buttons and customization in available or not functionality
| SpokePhone | Owner | http://spokephone.craftedium.xyz/ | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000305299 | 0 | 2017-09-20 | 2017-10-06 |  |  | Passed | Client want to 2nd phase embeding on site he want to 1) Show two tables of data to visitors that relate to the costs they will have to take and make a call in their selected country. 2) New page on the site to allow people to work out their Total Cost of Ownerwhip (TCO), and see typical ROI. | New page on the site to allow people to work out their Total Cost of Ownerwhip (TCO), and see typical ROI.
2017-10-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| PropertiMatch | Owner | http://propertimatch.craftedium.xyz | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000058119 | 0 | 2017-07-10 | 2017-07-29 |  |  | Passed | Admin panel bugs,seller and buyer dashboard,payment system and searching module in laravel project | Seller and buyer dashboard module and chat between seller and buyer and integerate strip payment module in this site | custom vaidation of form and gallery
| SpokePhone | Owner | http://spokephone.craftedium.xyz/ | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000305299 | 0 | 2017-09-20 | 2017-10-06 |  |  | Passed | Client want to 2nd phase embeding on site he want to 1) Show two tables of data to visitors that relate to the costs they will have to take and make a call in their selected country. 2) New page on the site to allow people to work out their Total Cost of Ownerwhip (TCO), and see typical ROI. | New page on the site to allow people to work out their Total Cost of Ownerwhip (TCO), and see typical ROI.
| Piedpipertravel-DL | Contributor | http://portal.fleekbiz.com/projectID/flyer.jpg | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000317093 | 0 | 2017-10-02 | 2017-10-12 |  |  | Passed | 1) Fix my login as it seems corrupted. It logs me in ok, but then it keeps asking me to login again! 2) Adding the ability to delete and edit existing reservation forms and information forms.
| Call Me Loco | Contributor | http://callmeloco.com | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000293061 | 0 | 2017-10-26 | 2017-10-26 |  |  | Passed | The email response template will be sent as a reply to them. In the email response template, we have 3 fields which need to be filled automatically through website DB. When someone fills out the form on Callmeloco.com/promo. The three fields including NAME, Login, Password. The website is going to take the name from The form that will be filled from the customer. the website will take the login and password from the Excel sheet that I attached
| Trend Box | Owner | http://trendbox.craftedium.xyz/ | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000408031 | 0 |  |  |  |  | Passed | Trendbox is a membership website based on monthly subscriptions for the users. User will have to sign up to access the website and they will get access to their dashboard to further explore the website.this part is wrong. They can explore any part of the website except “get one pages” and the user control panel pages. Users will use the dashboard to answer “user preferences” questions and to like “loved items” (will be added by admin). Users could also see their past deliveries and if they want to return any products then they could use “refund option” under same section of the website. This is overall concept of the website.
2017-11-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| Piedpipertravel-DL | Contributor | http://portal.fleekbiz.com/projectID/flyer.jpg | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000317093 | 0 | 2017-10-02 | 2017-10-12 |  |  | Passed | 1) Fix my login as it seems corrupted. It logs me in ok, but then it keeps asking me to login again! 2) Adding the ability to delete and edit existing reservation forms and information forms.
| PropertiMatch | Owner | http://propertimatch.craftedium.xyz | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000058119 | 0 | 2017-07-10 | 2017-07-29 |  |  | Passed | Admin panel bugs,seller and buyer dashboard,payment system and searching module in laravel project | Seller and buyer dashboard module and chat between seller and buyer and integerate strip payment module in this site | custom vaidation of form and gallery
| Trend Box | Owner | http://trendbox.craftedium.xyz/ | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000408031 | 0 |  |  |  |  | Passed | Trendbox is a membership website based on monthly subscriptions for the users. User will have to sign up to access the website and they will get access to their dashboard to further explore the website.this part is wrong. They can explore any part of the website except “get one pages” and the user control panel pages. Users will use the dashboard to answer “user preferences” questions and to like “loved items” (will be added by admin). Users could also see their past deliveries and if they want to return any products then they could use “refund option” under same section of the website. This is overall concept of the website.
2017-12-01
| Project/Tasks Name | Role | URL to check | Project Portal Link | # of Revisions | Assigned Start Date | Assigned End Date | Actual Start Date | Actual End Date | QA Result | Summary of Work done | Challenges Faced | Extra Efforts (if any) | RA Comments (optional) | Management Comments (optional)
| PropertiMatch | Owner | http://propertimatch.craftedium.xyz | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000058119 | 0 | 2017-07-10 | 2017-07-29 |  |  | Passed | Working on client new requriements . | Merging old functionality with new functionality
| Trend Box | Owner | http://trendbox.craftedium.xyz/ | https://projects.zoho.com/portal/fleekbiz#todomilestones/1081581000000408031 | 0 |  |  |  |  | Passed | Working on client new changes
Note on D6: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F6: Created by Resource
Note on D54: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F54: Created by Resource
Note on D102: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F102: Created by Resource
Note on D150: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F150: Created by Resource
Note on D198: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F198: Created by Resource
Note on D246: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F246: Created by Resource
Note on D294: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F294: Created by Resource
Note on D342: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F342: Created by Resource
Note on D390: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F390: Created by Resource
Note on D438: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F438: Created by Resource
Note on D486: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F486: Created by Resource
Note on D534: Could be any of following: - Source file - Document - Staging or live links - Reports links
Note on F534: Created by Resource

## Variables
QA Result | Department | Role
N/A | Management | Owner
Failed | Development | Contributor
Passed | Design
Writing
Marketing
Sales
HR
Support